## Project Milestone
PROJECT MILESTONE
Date | Activity | Note
2015-06-15 | Start project | 10
2015-06-26 | Specification document/ architecture design | -10
2015-07-10 | Release version 0.1 | 10
2015-07-24 | Release version 0.2 | -10
2015-08-07 | Deploy project | 10
Sprint | From date | End date | Output
1 | 2015-06-15 | 2015-06-26 | Gather requirements
Finish requirement document
Design flow business
Design flow IT
Design system architecture
2 | 2015-06-29 | 2015-07-10 | Client register page
Student register page
Log in page
Database set up
Client home page.
Student home page.
3 | 2015-07-13 | 2015-07-24 | Search job offers.
Post job offers.
Recommend students
Apply for job offer.
Bookmark offers.
Notification system.
4 | 2015-07-27 | 2015-08-07 | Intergration Test
UAT
Bug fixes
Finish documents